## FY 2018-19
FY 2018/19
Agency: | MORENO VALLEY
Prepared by: | Launa Jimenez
Phone #: | (951) 413-3128
Date: | 2018-03-26
|  |  | FY 2016/17 Audited Measure A Balance: | 5135340
|  |  | FY 2017/18 (Revised) Measure A Revenue: | 3912000
|  |  | FY 2017/18 Project Status Report expenses: | 5547466.5
|  |  | Estimated Prior Year Measure A Balance: | 3499873.5
|  |  | Estimated FY 2018/19 Measure A Allocation: | 4025000
|  |  | Estimated Measure A Available for FY 2018/19 Projects: | 7524873.5
Item No. | Project Name / Limits | Project Type | Total Project Cost | Measure A Funds | Project # | FY 17/18 Total Budget | Total budget used as of 3/13 | FY 17/18 Measure A Budget | FY 17/18 Estimated used Measure A | Estimated Measure A Balance
2018/19
2019-01 | Public Works - Capital Projects Program Budget | Program Budget | 263654 | 263654
2019-02 | Public Works - Sign/Striping | Operating Budget | 1223250 | 1223250
2019-03 | Public Works - Tree Trimming | Operating Budget | 496261 | 496261
2019-04 | Transfers to 2013-2014 Refunding Lease Revenue Bonds | Debt Service | 1055000 | 1055000
2019-05 | Transfers to TRIP Debt Service | Debt Service | 1491000 | 1491000
2019-06 | Alessandro Blvd at Chagall Ct and at Graham St | Street Improvements | 175911 | 17591.1 | 801 0057 | 586370 | 19014.78 | same |  | 10% local match | Henry | 30% of $586,370 = $175,911
2019-07 | Alessandro Blvd/ Elsworth St Intersection Imprv | Street Improvements | 790000 | 6684.8 | 801 0047 | 1049328 | 769093.7 | 766848 | 700000 | 66848 | Marge | $5,000 needed for warranty walk
2019-08 | Annual ADA Compliant Curb Ramp Upgrades | Street Improvements | 303964 | 223964 | 801 0008 | 440964 | 9431.88 | 240964 | 17000 | 223964 | Guy
2019-09 | Bike Lane Improvements | Street Improvements (Bike Lanes) | 84755 | 42377.5 | 801 0049 | 109755 | 72.25 | 109755 | 25000 | 84755 | Eric
2019-10 | Citywide Annual Pavement Resurfacing | Street Improvements | 223596 | 223596 | 801 0003 | 263596 | 28322.51 | 263596 | 40000 | 223596 | Quang
2019-11 | Cycle 1 ATP Citywide SRTS Pedestrian Facility Improvements | Street Improvements | 1200000 | 6404 | 801 0063 | 1579662 | 84556.01 | 6404 | 0 | 6404 | Quang
2019-12 | Gentian Ave and Eucalyptus Ave Class II Bike Lanes | Street Improvements | 43691 | 18000 | 801 0079 | 70000 | 0 | 18000 |  | 18000 | Eric
2019-13 | Heacock St/ Perris Vally Storm Drain Lateral A to Cactus Ave | Street Improvements | 74611 | 74611 | 801 0023 | 853496 | 502792.25 | 269780 | 195169 | 74611 | Henry | $5,000 needed for warranty walk
2019-14 | Heacock St South Extension | Street Improvements | 925000 | 15000 | 801 0010 | 952000 | 10980.38 | 30000 | 15000 | 15000 | Marge
2019-15 | Property Acquisition for Street Purposes | Street Improvements | 1000 | 1000 | 801 0065 | 16083 | 4142.2 | 16083 | 15083 | 1000 | Josh
2019-16 | Residential Traffic Management Program (Speed Humps) | Street Improvements | 107675 | 7675 | 801 0015 | 124675 | 37384.52 | 74675 | 67000 | 7675 | John
2019-17 | SR-60/ Theodore St Interchange | Street Improvements | 2130000 | 305939 | 801 0052 | 2344066 | 13813.19 | 505939 | 200000 | 305939 | Marge
2019-18 | Moreno Townsite Area Storm Drain & Street Improvements/ Alessandro Blvd to Drainage Facility | Street Improvements | 3725000 | 383577 | 801 0011 | 3809308 | 22092.48 | 1609308 | 75000 | 1534308 | Quang
2019-19 | Heacock St Channel Improvements | Drainage | 291965 | 6533 | 804 0001 | 305498 | 0 | 13533 | 7000 | 6533 | Henry
2019-20 | Hubbard St Storm Drain Line H-1A Stage 3 | Drainage | 5000 | 5000 | 804 0010 | 1540204 | 1187959.81 | 100552 | 95552 | 5000 | Henry | $5,000 needed for warranty walk
2019-21 | San Timoteo Foothill Storm Drain K-1 and K-4 (ADP) | Drainage | 2100000 | 260169.25 | 804 0007 | 2188787 | 38470.59 | 1110677 | 70000 | 1040677 | Quang
2019-22 | Dynamic Traveler Alert Message Boards | Traffic Enhancements | 382000 | 5516 | 808 0016 | 432716 | 21598.48 | 37516 | 32000 | 5516 | John
2019-23 | Dynamic Traveler Alert Message Boards | Traffic Signals | 380000 | 43928 | 808 0016 | 432716 | 21598.48 | 385000 | 0 | 11.56% local match | John
2019-24 | ITS Deployment Phase 1B | Traffic Signals | 2141236 | 287996.242 | 808 0015 | 2341236 | 99481.52 | 2195000 | 0 | 13.45% local match | John
2019-25 | Pedestrian Hybrid Beacon on Cactus Ave at Woodland Park | Traffic Signals | 203993 | 203993 | 808 0017 | 203993 | 0 | 203993 | 0 | 203993 | John
2019-26 | Systemic Safety Analysis Report Program | Traffic Signals | 148000 | 13000 | 808 0032 | 150000 | 0 | 15000 | 2000 | 13000 | John
2019-27 | Traffic Signal Equipment/ Upgrades | Traffic Signals | 41804 | 41804 | 808 0013 | 51804 | 7286.88 | 51804 | 10000 | 41804 | John
|  | TOTAL | 20008366 | 6723523.892
FUND 2301 - Capital Projects Grants
The FY 14/15 transfer of $1,495,760 from Measure A (Fund 2001) to Capital Projects Grant (Fund 2301) provided local match funding for the following grant awards. The FY 17/18 budgets and expenditures in Capital Projects Grants do not impact the Measure A fund. Any unused local match funds will be transferred back to the Measure A fund upon project completion.
801349.608

## FY 2019-20
FY 2019/20
Agency: | MORENO VALLEY
Prepared by: | Launa Jimenez
Phone #: | (951) 413-3128
Date: | 2018-03-26
|  |  | Estimated Prior Year Measure A Balance: | 801349.608
|  |  | Estimated FY 2019/20 Measure A Allocation: | 4106000
|  |  | Estimated Measure A Available for FY 2019/20 Projects: | 4907349.608
Item No. | Project Name / Limits | Project Type | Total Project Cost | Measure A Funds
2019/20
2020-01 | Public Works - Capital Projects Program Budget | Program Budget | 263654 | 263654
2020-02 | Public Works - Sign/Striping | Operating Budget | 1223250 | 1223250
2020-03 | Public Works - Tree Trimming | Operating Budget | 496261 | 496261
2020-04 | Transfers to 2013-2014 Refunding Lease Revenue Bonds | Debt Service | 1055000 | 1055000
2020-05 | Transfers to TRIP Debt Service | Debt Service | 1491000 | 1491000
|  | TOTAL | 4529165 | 4529165
378184.608

## FY 2020-21
FY 2020/21
Agency: | MORENO VALLEY
Prepared by: | Launa Jimenez
Phone #: | (951) 413-3128
Date: | 2018-03-26
|  |  | Estimated Prior Year Measure A Balance: | 378184.608
|  |  | Estimated FY 2020/21 Measure A Allocation: | 4209000
|  |  | Estimated Measure A Available for FY 2020/21 Projects: | 4587184.608
Item No. | Project Name / Limits | Project Type | Total Project Cost | Measure A Funds
2020/21
2021-01 | Public Works - Capital Projects Program Budget | Program Budget | 263654 | 263654
2021-02 | Public Works - Sign/Striping | Operating Budget | 1223250 | 1223250
2021-03 | Public Works - Tree Trimming | Operating Budget | 496261 | 496261
2021-04 | Transfers to 2013-2014 Refunding Lease Revenue Bonds | Debt Service | 1055000 | 1055000
2021-05 | Transfers to TRIP Debt Service | Debt Service | 1491000 | 1491000
|  | TOTAL | 4529165 | 4529165
58019.608

## FY 2021-22
FY 2021/22
Agency: | MORENO VALLEY
Prepared by: | Launa Jimenez
Phone #: | (951) 413-3128
Date: | 2018-03-26
|  |  | Estimated Prior Year Measure A Balance: | 58019.608
|  |  | Estimated FY 2021/22 Measure A Allocation: | 4314000
|  |  | Estimated Measure A Available for FY 2021/22 Projects: | 4372019.608
Item No. | Project Name / Limits | Project Type | Total Project Cost | Measure A Funds
2021/22
2022-01 | Public Works - Capital Projects Program Budget | Program Budget | 263654 | 263654 |  |  | What-If Analysis: Data Tab
2022-02 | Public Works - Sign/Striping | Operating Budget | 1223250 | 1107041.25 | 90.5% | -116208.75 | 1. 100% in cell to the right (G16)
2022-03 | Public Works - Tree Trimming | Operating Budget | 496261 | 449116.205 | 90.5% | -47144.795 | 2. Cell G16 (= G15)
2022-04 | Transfers to 2013-2014 Refunding Lease Revenue Bonds | Debt Service | 1055000 | 1055000 |  | -163353.545 | 3. Change formula in F15 and F16; number cell * percentage cell (E16*G16)
2022-05 | Transfers to TRIP Debt Service | Debt Service | 1491000 | 1491000 |  |  | 4. Cell H15 (F15-E15); Cell H16 (F16-E16)
|  | TOTAL | 4529165 | 4365811.455 |  |  | 5. Cell H17 (H15+H16)
6. What-If Analysis - Goal Seek
|  |  |  | 6208.153 |  |  | 7. Set Cell: H17
8. To Value: Difference between F10 and F19
9. By Changing Cell: G16

## FY 2022-23
FY 2022/23
Agency: | MORENO VALLEY
Prepared by: | Launa Jimenez
Phone #: | (951) 413-3128
Date: | 2018-03-26
|  |  | Estimated Prior Year Measure A Balance: | 6208.153
|  |  | Estimated FY 2022/23 Measure A Allocation: | 4422000
|  |  | Estimated Measure A Available for FY 2022/23 Projects: | 4428208.153
Item No. | Project Name / Limits | Project Type | Total Project Cost | Measure A Funds
2022/23
2023-01 | Public Works - Capital Projects Program Budget | Program Budget | 263654 | 263654 |  |  | What-If Analysis: Data Tab
2023-02 | Public Works - Sign/Striping | Operating Budget | 1223250 | 1149855 | 94% | -73395 | 1. 100% in cell to the right (G16)
2023-03 | Public Works - Tree Trimming | Operating Budget | 496261 | 466485.34 | 94% | -29775.66 | 2. Cell G16 (= G15)
2023-04 | Transfers to 2013-2014 Refunding Lease Revenue Bonds | Debt Service | 1055000 | 1055000 |  | -103170.66 | 3. Change formula in F15 and F16; number cell * percentage cell (E16*G16)
2023-05 | Transfers to TRIP Debt Service | Debt Service | 1491000 | 1491000 |  |  | 4. Cell H15 (F15-E15); Cell H16 (F16-E16)
|  | TOTAL | 4529165 | 4425994.34 |  |  | 5. Cell H17 (H15+H16)
6. What-If Analysis - Goal Seek
|  |  |  | 2213.813 |  |  | 7. Set Cell: H17
8. To Value: Difference between F10 and F19
9. By Changing Cell: G16

## Project Status Report FY17-18
PROJECT STATUS REPORT FY 2017/18
Agency: | MORENO VALLEY
Prepared by: | Launa Jimenez
Phone #: | (951) 413-3128
Date: | 2018-03-26
Item No. | Project Name / Limits | Project Type | Total Cost | Anticipated Measure A Funds Expended (Est thru 6/30/2018) | Estimated/ Actual Completion | Status | Project # | Measure A Budget | Measure A Budget used as of 3/6 | Measure A Encumbrance as of 3/6 | Measure A Remaining Balance | E-Suites | Grant
1 | Measure A Program Budget | Program Budget | 383619 | 383619 | N/A | Annual Budget
2 | Public Works - Sign/Striping | Operating Budget | 1176903 | 1176903 | N/A | Annual Budget
3 | Public Works - Tree Trimming | Operating Budget | 475660 | 475660 | N/A | Annual Budget
4 | Transfers to 2013/2014 Refunding Lease Revenue Bonds | Debt Service | 1058000 | 1058000 | N/A | Annual Budget
5 | Transfers to TRIP Debt Service | Debt Service | 1489000 | 1489000 | N/A | Annual Budget
6 | Alessandro Blvd at Chagall Ct and at Graham St | Street Improvements | 586370 | 41045.9 | 2018-07-01 | Pre-Construction | 801 0057 | 10% local match | *Henry advises we will use 70%; $586,370*70% = $410,459; $410,459*10% = $41,046
7 | Transfer from 801 0011 (2001) to 801 0057 (2301) Alessandro Blvd at Chagall Ct and at Graham St | Street Improvements | 586370 | 45501 | 2018-07-18 | Pre-Construction |  | 45501 | 45501 |  | 0
8 | Alessandro Blvd/ Elsworth St Intersection Imprv | Street Improvements | 1049328 | 70000 | 2018-04-01 | Construction | 801 0047 | 766848 X 10% = 76,684.80 | 648638.76 | 141879.19 | -23669.95 | YES | Yes 10% Match | Marge
9 | Annual ADA Compliant Curb Ramp Upgrades | Street Improvements | 440964 | 17000 | N/A | On-going Annual Project | 801 0008 | 240964 | 9431.88 | 7962.5 | 223569.62 | YES |  | Guy
10 | Aqueduct Trail | Street Improvements | 226167 | 17733.4 | 2018-06-01 | PA/ED Phase | 801 0055 | 20% local match | *Henry advises we will use all of it; 2301 budget is $88,667
11 | Bike Lane Improvements | Street Improvements (Bike Lanes) | 109755 | 12500 | 2018-12-01 | Construction | 801 0049 | 109755 X 50% = 54,877.50 | 72.25 | 11647.2 | 98035.55 | YES | Yes 50% Match | Eric
12 | Citywide Annual Pavement Resurfacing | Street Improvements | 263596 | 40000 | N/A | On-going Annual Project | 801 0003 | 263596 | 28322.51 | 16110 | 219163.49 | YES |  | Quang
13 | Cycle 1 ATP Citywide SRTS Pedestrian Facility Improvements | Street Improvements | 1579662 | 0 | 2018-12-01 | Construction | 801 0063 | 6404 | 0 | 0 | 6404 |  |  | Quang
14 | Gentian Ave and Eucalyptus Ave Class II Bike Lanes | Street Improvements | 70000 | 0 | 2018-12-01 | Design | 801 0079 | 18000 | 0 | 0 | 18000 |  |  | Eric
15 | Heacock St/ Perris Vally Storm Drain Lateral A to Cactus Ave | Street Improvements | 853496 | 195169 | 2018-05-01 | Construction | 801 0023 | 269780 | 55169.91 | 0 | 214610.09 | YES |  | Henry
16 | Heacock St South Extension | Street Improvements | 952000 | 15000 | 2020-12-01 | PE/ Environmental Clearance | 801 0010 | 30000 | 46.13 | 0 | 29953.87 |  |  | Marge
17 | Property Acquisition for Street Purposes | Street Improvements | 16083 | 15083 | N/A | On-going Annual Project | 801 0065 | 16083 | 4142.2 | 11000 | 940.8 | YES |  | Josh
18 | Reche Vista Dr Realignment/ Perris Blvd/ Heacock St to NCL | Street Improvements | 5770 | 3000 | 2018-03-01 | Completed | 801 0009 | 5770 | 2824.6 | 0 | 2945.4 | YES |  | Quang
19 | Residential Traffic Management Program (Speed Humps) | Street Improvements | 124675 | 67000 | N/A | On-going Annual Project | 801 0015 | 74675 | 37384.52 | 30600 | 6690.48 | YES |  | John
20 | SR-60/ Theodore St Interchange | Street Improvements | 2344066 | 200000 | 2023-12-01 | PE/ Environmental Clearance | 801 0052 | 505939 | 9429.07 | 595578.37 | -99068.44 | YES |  | Marge
21 | Moreno Townsite Area Storm Drain & Street Improvements/ Alessandro Blvd to Drainage Facility | Street Improvements | 3809308 | 18750 | 2019-06-01 | Design | 801 0011 | 1408038 X 25% = 352,009 Grant 201,270 Measure A | $22,092.48 $0 | $75.18 $0 | $1,385,870.34 $201,270 | YES | Yes 25% Match | Quang
22 | Cottonwood Basin | Drainage | 127258 | 25000 | 2018-07-01 | Construction | 804 0013 | 25000 | 0 | 25000 | 0 |  |  | Henry
23 | Heacock St Channel Improvements | Drainage | 305498 | 7000 | 2019-12-01 | Construction | 804 0001 | 13533 | 0 | 2710.36 | 10822.64 |  |  | Henry
24 | Hubbard St Storm Drain Line H-1A Stage 3 | Drainage | 1540204 | 95552 | 2018-06-01 | Construction | 804 0010 | 100552 | 47006.18 | 48146.76 | 5399.06 |  |  | Henry
25 | San Timoteo Foothill Storm Drain K-1 and K-4 (ADP) | Drainage | 2188787 | 17500 | 2019-06-01 | Design | 804 0007 | 1110677 X 25% = 277,669.25 | 38470.59 | 62419.81 | 1009787 | YES | Yes 25% Match | Quang
26 | Dynamic Traveler Alert Message Boards | Traffic Enhancements | 432716 | 32000 | 2018-12-01 | Design | 808 0016 | 37516 | 21598.48 | 15917.52 | 0 |  |  | John
27 | Dynamic Traveler Alert Message Boards | Traffic Signals | 432716 | 3597 | 2018-12-01 | Design | 808 0016 | 11.56% local match | *John advised we will use $52,716 total; 3/14 we have used $21,598.48 of Measure A; $31,117*11.56% = $3,597
28 | ITS Deployment Phase 1B | Traffic Signals | 2341236 | 7231 | 2018-12-01 | Design | 808 0015 | 13.45% local match | *John advised we will use $200,000 total; $200,000 - $146,236 = $53,764; $53,764*13.45% = $7,231.25
29 | Pedestrian Hybrid Beacon on Cactus Ave at Woodland Park | Traffic Signals | 203993 | 0 | On Hold | On Hold | 808 0017 | 203993 | 0 | 0 | 203993 | YES |  | John
30 | Systemic Safety Analysis Report Program | Traffic Signals | 150000 | 2000 | 2019-06-01 | Advertising Consultant | 808 0032 | 15000 | 0 | 0 | 15000 |  |  | John
31 | Traffic Signal Equipment/ Upgrades | Traffic Signals | 51804 | 10000 | N/A | On-going Annual Project | 808 0013 | 51804 | 7286.88 | 7713.12 | 36804 | YES |  | John
32 | Safe Routes to School Outreach Program | Public Outreach | 114992 | 6622.2 | 2017-12-01 | Completed | 801 0056 | 10% local match | *Actual Exp $66,222.76
|  | TOTAL | 25489996 | 5547466.5
FUND 2301 - Capital Projects Grants
The FY 14/15 transfer of $1,495,760 from Measure A (Fund 2001) to Capital Projects Grant (Fund 2301) provided local match funding for the following grant awards. The FY 15/16 budgets and expenditures in Capital Projects Grants do not impact the Measure A fund. Any unused local match funds will be transferred back to the Measure A fund upon project completion.
Note on L16: Launa Jimenez: $112,640 removed because of O'Duffy PO (encumbrance did not change with A/P change)

## Sheet1 (hidden)
BANNING
BEAUMONT
BLYTHE
CALIMESA
CANYON LAKE
CATHEDRAL CITY
COACHELLA
CORONA
DESERT HOT SPRINGS
EASTVALE
HEMET
INDIAN WELLS
INDIO
JURUPA VALLEY
LA QUINTA
LAKE ELSINORE
MENIFEE
MORENO VALLEY
MURRIETA
NORCO
PALM DESERT
PALM SPRINGS
PERRIS
RANCHO MIRAGE
RCTC Regional Arterial
RIVERSIDE
RIVERSIDE COUNTY-CV
RIVERSIDE COUNTY-PVV
RIVERSIDE COUNTY-WESTERN
SAN JACINTO
TEMECULA
WILDOMAR

## Projections
RIVERSIDE COUNTY TRANSPORTATION COMMISSION
MEASURE A PROGRAM ALLOCATION (PROJECTION)
% increase |  |  |  | 2% | 2.5% | 2.5% | 2.5%
Column1 | Audited Balance FY17 (Revised)³ | FY 2017/18 | FY 2018/19 | FY 2019/20 | FY 2020/21 | FY 2021/22 | FY 2022/23
Western County
BANNING | 1768949 | 564000 | 586000 | 598000 | 613000 | 628000 | 644000
BEAUMONT | 0 | 590000 | 921000 | 939000 | 962000 | 986000 | 36831
CALIMESA | 566862 | 158000 | 167000 | 170000 | 174000 | 178000 | 182000
CANYON LAKE | 324917 | 177000 | 185000 | 189000 | 194000 | 199000 | 204000
CORONA | 10882442 | 4036000 | 4143000 | 4226000 | 4332000 | 4440000 | 4551000
EASTVALE | 4677775 | 1282000 | 1317000 | 1343000 | 1377000 | 1411000 | 1446000
HEMET | 5336943 | 1692000 | 1767000 | 1802000 | 1847000 | 1893000 | 1940000
JURUPA VALLEY | -120363 | 1937000 | 36571 | 2055000 | 2106000 | 2159000 | 2213000
LAKE ELSINORE | 1545370 | 1308000 | 1354000 | 1381000 | 1416000 | 1451000 | 1487000
MENIFEE | 2791713 | 1660000 | 1731000 | 1766000 | 1810000 | 1855000 | 1901000
MORENO VALLEY | 5135340 | 3912000 | 4025000 | 4106000 | 4209000 | 4314000 | 4422000
MURRIETA | 7150588 | 2349000 | 2431000 | 2480000 | 2542000 | 2606000 | 2671000
NORCO | 2060218 | 657000 | 679000 | 693000 | 710000 | 728000 | 746000
PERRIS | 4928089 | 1508000 | 1630000 | 1663000 | 1705000 | 1748000 | 1792000
RIVERSIDE | 17852987 | 7438000 | 7663000 | 7816000 | 36838 | 8211000 | 8416000
SAN JACINTO | 3235105 | 854000 | 879000 | 897000 | 919000 | 942000 | 966000
TEMECULA | 6251531 | 2993000 | 3184000 | 3248000 | 3329000 | 3412000 | 3497000
WILDOMAR | 275786 | 617000 | 641000 | 654000 | 670000 | 687000 | 704000
RIVERSIDE COUNTY-WESTERN | 435510 | 5327000 | 5523000 | 5633000 | 5774000 | 5918000 | 6066000
RCTC Regional Arterial¹ |  | 295000 | - | - | - | - | -
SUBTOTAL-Western County |  | 39354000 | 40841000 | 41659000 | 42700000 | 43766000 | 44859000
Coachella Valley
CATHEDRAL CITY | 446496 | 1493000 | 1490000 | 1520000 | 1558000 | 1597000 | 1637000
COACHELLA | 1263691 | 615000 | 608000 | 620000 | 636000 | 652000 | 668000
DESERT HOT SPRINGS | 45572 | 476000 | 477000 | 487000 | 499000 | 511000 | 524000
INDIAN WELLS | 20520 | 237000 | 266000 | 271000 | 278000 | 285000 | 292000
INDIO | 725555 | 1907000 | 1957000 | 1996000 | 2046000 | 2097000 | 2149000
LA QUINTA | 854791 | 1481000 | 1525000 | 1556000 | 1595000 | 1635000 | 1676000
PALM DESERT | 21545267 | 2718000 | 2798000 | 2854000 | 2925000 | 2998000 | 3073000
PALM SPRINGS | 7369067 | 2051000 | 2118000 | 2160000 | 2214000 | 2269000 | 2326000
RANCHO MIRAGE | 3349388 | 893000 | 924000 | 942000 | 966000 | 990000 | 36540
RIVERSIDE COUNTY-CV | 918044 | 1780000 | 1771000 | 1806000 | 1851000 | 1897000 | 1944000
CVAG² |  | - | - | - | - | - | -
SUBTOTAL-Coachella Valley |  | 13651000 | 13934000 | 14212000 | 14568000 | 14931000 | 15304000
Palo Verde Valley
BLYTHE | 2332281 | 844000 | 779000 | 795000 | 815000 | 835000 | 856000
RIVERSIDE COUNTY-PVV | 381889 | 193000 | 189000 | 193000 | 198000 | 203000 | 208000
SUBTOTAL-Palo Verde Valley |  | 1037000 | 968000 | 988000 | 2000-01-13 | 1038000 | 1064000
TOTAL |  | 54042000 | 55743000 | 56859000 | 58281000 | 59735000 | 61227000
¹ Beaumont became eligible for Measure A local streets and roads funds in November 2017; its share prior to effective date is allocated to the Western County Measure A Regional Arterial fund.
² Under an agreement between CVAG and La Quinta, CVAG receives 50% of La Quinta's allocation and La Quinta the remaining 50% until such time La Quinta has reimbursed CVAG for TUMF fees CVAG would have received from La Quinta if La Quinta had joined the TUMF program when the TUMF was established.
³Audited Balance shown is from draft report and may be revised in final report
Note: Estimate for Planning Purposes, subject to change and rounding differences